## 15th October to 20th October
DATE | PARTICULARS | DEPARTMENT | NEW SCREEN /EXISTING SCREEN CHANGE (Please write the name of the screen) | DATABASE CHANGES IF YES THEN IN WHICH TABLE | Status
15/10/2012 | Added "Upload Document" functionality in the page / Changed order of fields, changes have been done as per client, Primary level QC done, yet to be verified by client. | Dispatch | new screen/ inward register | Yes / Table Name : InwardRegister | Done
16/10/2012 | New page has been added to application named Worksheet Register for managing details of inward changes have been done as per client, Primary level QC done, yet to be verified by client. | Common | new screen/worksheet register | Yes / Table Name : WorksheetRegister | Done
17/10/2012 | New page has been added to application named File Register for managing file details of each letter changes have been done as per client, Primary level QC done, yet to be verified by client. | Common | new screen/ file register | Yes / Table Name : File | Done
18/10/2012 | New Page has been added to application named Outward Register with new formats - Added officeMaster / Office types in the database changes have been done as per client, Primary level QC done, yet to be verified by client. | Dispatch | new screen/ outward register | Yes / Table Name : OutwardRegister / OfficeTypes / Offices | Done
19/10/2012 | New page has been added to application named Govt Docs Register - Insert / Update completed - Testing In progress | Common | new screen/ govt docs register | Yes / Table Name : GovtDocRegister | In Progress
20/10/2012 | New page has been added to application named SO File Register - Insert / Update completed - Testing In progress | Common | new screen/ So File | Yes / Table Name : SORegister | In Progress

## 22nd october to 27th October
DATE | PARTICULARS | DEPARTMENT | NEW SCREEN /EXISTING SCREEN CHANGE (Please write the name of the screen) | DATABASE CHANGES IF YES THEN IN WHICH TABLE | Status
22/10/2012 | New page has been added to application named MLA / Minister Regsiter- Insert / Update completed - Testing In progress | Common | new screen/ MLA-mp-minister register | Yes / Table Name : MLARegister | Done
23/10/2012 | New page has been added to application named Vidhansabha Tarankit register- Insert / Update completed - Testing In progress | Common | new screen/Vidhansabha tarankit register | Yes / Table Name : VidhansabhaRegister | Done
24/10/2012 | Added "Upload Document" functionality in the page / Changed order of fields | Dispatch | existing screen/ Inward Register | Yes / Table Name: Inward Register | Done
25/10/2012 | New page has been added to application named Worksheet Register for managing details of inward | Common | existing screen/ worksheet register | Yes / Table Name : WorkSheetRegister | Done
26/10/2012 | New page has been added to application named File Register for managing file details of each letter | Common | new screen/ file register | Yes / Table Name : File | Done
| New Page has been added to application named Outward Register with new formats - Added officeMaster / Office types in the database | Common | new screen/ outward register | Yes / Table Name : OutwardRegister / OfficeTypes / Offices | Done
27/10/2012 | New page has been added to application named Govt Docs Register - Insert / Update completed | Common | existing screen/ govt docs completed | Yes / Table Name : GovtDocs | Done
| New page has been added to application named SO File Register - Insert / Update completed | Common | existing screen/ SO file done | Yes / Table Name : SOFile | Done

## 29th October to 3rd November
DATE | PARTICULARS | DEPARTMENT | NEW SCREEN /EXISTING SCREEN CHANGE (Please write the name of the screen) | DATABASE CHANGES IF YES THEN IN WHICH TABLE | Status
| New page has been added to application named RTI Appeal register - insert / Update completed | Common | new screen/ RTI Appeal Register | Yes / Table Name : RTI | Done
| New page has been added to application named High Court Register- Insert/Update completed | Common | new Screen/ High court Register | Yes / Table Name : HighCourtReg | Done
| New page has been added to application named PIO & APIO Register- Insert/Update completed | Common | new screen/ PIO-APIO Register | Yes / Table Name : PIO | Done
| New page has been added to application named Vigilance Register- Insert/Update completed | Common | new screen/ Vigilance register | Yes / Table Name : Vigilance | Done
| New page has been added to application named Appeal register - insert / Update completed | CCRA Legal | new screen/ Appeal Register | Yes | Done
| New page has been added to application named Sunavni register - insert / Update completed | CCRA Legal | new screen/ Sunavni Register | Yes | Done
| New page has been added to application named No Record certificate register - insert / Update completed | Record & Marriage Department |  | Yes | Done
| New page has been added to application named Marriage Certificate copy application register - insert / Update completed | Record & Marriage Department | new screen / Marriage Certificate copy application Reg. | Yes | Done
| New page has been added to application named APPLICATION DISPOSAL REGISTER. - insert / Update completed | Record & Marriage Department | new screen /APPLICATION DISPOSAL REGISTER | Yes | Done

## 5th Nov to 9th Nov
DATE | PARTICULARS | DEPARTMENT | NEW SCREEN /EXISTING SCREEN CHANGE (Please write the name of the screen) | DATABASE CHANGES IF YES THEN IN WHICH TABLE | Status
| Dead stock Register | Record & Marriage Department | new | Yes | Done
| Library Register | Record & Marriage Department | new | Yes | Done
| Lekhan Samagri | Record & Marriage Department | new | Yes | Done
| Kalpataru purchase Register | Record & Marriage Department | new | Yes | Done
| Book Forms Register | Record & Marriage Department | new | Yes | Done
| Diary | Inspection Department | new | Yes | Done
| Sealing | Inspection Department | new | Yes | Done

## 16th nov to 29th nov
DATE | PARTICULARS | DEPARTMENT | NEW SCREEN /EXISTING SCREEN CHANGE (Please write the name of the screen) | DATABASE CHANGES IF YES THEN IN WHICH TABLE | Status
| ACB Case Register | Establishment Department | NEW | ACB_CaseRegister | Done
| C.L. Card | Establishment Department | NEW | C_L_Card | Done
| Departmental Inquiry Register | Establishment Department | NEW | Departmental_Inquiry_Register | Done
| Fajal Register | Establishment Department | NEW | FajalRegister | Done
| Mahekam Register | Establishment Department | NEW | MahekamRegister | Done
| Roster Register | Establishment Department | NEW | RosterRegister | Done
| TransferApplicationRegister | Establishment Department | NEW | Transfer_Appl_Register | Done
| Government Documents | Administration Department | CHANGE IN EXISTING | GovtDocs | Done
| High Court Register | Administration Department | CHANGE IN EXISTING | HighcourtReg | Done
| MLA and Minister Register | Administration Department | CHANGE IN EXISTING | MLA | Done
| PIO | Administration Department | CHANGE IN EXISTING | PIO | Done
| PrimaryInvestigation-InquiryRegister | Administration Department | CHANGE IN EXISTING | InquiryRegister | Done
| RTIAppealRegister | Administration Department | CHANGE IN EXISTING | RTI | Done
| SOFile | Administration Department | CHANGE IN EXISTING | SOFILE | Done
| VidhansabhaTarankitQuestionRegister | Administration Department | CHANGE IN EXISTING | tarankit | Done
| VigilanceRegister | Administration Department | CHANGE IN EXISTING | Vigilance | Done
| File Register | Account Department | CHANGE IN EXISTING | FileRegister | Done
| WorkSheet Register | Account Department | CHANGE IN EXISTING | WorkSheetRegister | Done
| C.D. Register | ADM(Photo) Department | CHANGE IN EXISTING | CD_Register | Done
| Application Disposal Register | Record and Marriage | NEW | ApplicationDisposalRegister | Done
| BookFormsRegister | Record and Marriage | NEW | BookFormsRegister | Done
| Dead Stock Register | Record and Marriage | NEW | DeadStockRegister | Done
| Kalpataru Purchase Stock | Record and Marriage | NEW | Kalpataru_Purchase_Stock_Register | Done
| Lekhan Samagri | Record and Marriage | NEW | LekhanSamagriRegister | Done
| Library Register | Record and Marriage | NEW | LibraryRegister | Done
| Marriage Register | Record and Marriage | NEW | MarriageCertificate | Done
| Marriage Volume Register | Record and Marriage | NEW | MarriageVolumeListRegister | Done
| No Record Certificate Register | Record and Marriage | NEW | NoRecordCertificateregister | Done
| Outward Register | Inward-Outward | CHANGE IN EXISTING | OutwardRegister_Latest | Done
| Testing of Pages |  |  |  | In Progress
| Issue in Testing |  |  |  | In Progress
| Issue in Masters |  |  |  | In Progress

## 30 nov to 12 dec
DATE | LINKING OF MASTERS | DEPARTMENT NAME | NEW SCREEN/EXISTING SCREEN CHANGES | DATABASE CHANGES (If yes then Table Name) | STATUS
| Vendor Master | Masters | Changes in the .cs file and source code | VendorMaster | done
| Item Master | Masters | Changes in the .cs file and source code | ItemMaster | done
| Department Master | Masters | Changes in the .cs file and source code | DepartmentMaster | done
| Designation Master | Masters | Changes in the .cs file and source code | DesignationMaster | done
| Qualification Master | Masters | Changes in the .cs file and source code | PostalStampDenomMaster | done
| User Roles | User Role Management Master | Changes in the .cs file and source code | UsersInOfficeRoles | done
DATE | TESTING OF PAGES | DEPARTMENT NAME | REGISTER NAME | Changes in TESTING SHEET DOCUMENT | STATUS
| 1 | ADM Photo Department | C.D. Register | ADM Photo.xls | done
| 2 | Administration Department | File Register | all testing sheets.xls | done
|  |  | Goverment Document |  | done
|  |  | MLA and Minister Register |  | done
|  |  | Primary investigation - Inquiry Register |  | done
|  |  | RTI Appeal Register |  | done
|  |  | SO File |  | done
|  |  | Vidhansabha Tarankit Question Register |  | done
|  |  | Vigilance Register |  | done
|  |  | Worksheet Register |  | done
| 3 | CCRA Legal Department | Appeal Register | TESTING SHEET - CCRA Legal.xls | done
|  |  | Sunavni Register |  | done
| 4 | Establishment Department | Departmental Inquiry Register | Testing Establishment.xls | done
ACB Case Register
|  |  | Fajal Register |  | done
|  |  | Mahekam Register |  | done
|  |  | Roster Register |  | done
|  |  | Transfer Application Register |  | done
| 5 | Record and Marriage Department | Application Disposal Register | all testing sheets.xls | done
|  |  | Book Forms Register |  | done
|  |  | Dead Stock Register |  | done
|  |  | Kalpataru Register |  | done
|  |  | Lekhan Samagri Register |  | done
|  |  | Library Register |  | done
|  |  | Marriage Register |  | done
|  |  | Marriage Volume Regiaster |  | done
|  |  | No Record Certificate Register |  | done
| TESTING OF ALL ABOVE PAGES |  |  |  | done
| LIST OF QUESTIONS ABOUT INSERT FIELDS OF ALL REGISTERS |  |  |  | done
| ISSUES IN LINKING OF SOME MASTERS | Changes has to be made in master tables | changes to be made in source code and .cs file |  | progress

## 13 Dec To 18 Dec
DATE | LINKING OF MASTERS | DEPARTMENT NAME | NEW SCREEN/EXISTING SCREEN CHANGES | DATABASE CHANGES (If yes then Table Name) | STATUS
| Religion Master | Masters | Religion Master | No Changes | Done
| Caste Master | Masters | Caste Master | Cast_Master | Done
| District Master | Masters | District Master | No Changes | Done
| Taluka Master | Masters | Taluka Master | TalukaMaster | Done
| Recruitment Master | Masters | Recruitment Master | Recruitment_Master | Done
| Anamat Type Master | Masters | Anamat Type Master | AnamatMaster | Done